## Gamperaliya Monthly
Gamperaliya- Rapid Rural Development Programme - 2019 | [16 empty] | Annexure D
Physical and Financial Progress of the Month of marh 2019
District :
No | Name of the Project | Electorate | DS Division | GN Division |  | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [11 empty] | No. of Beneficiaries | Remarks
[5 empty] | Sector |  |  |  |  | Financial |  | Physical **
[10 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | supplying water line to the delgawatta road | kaluthara | kaluthara | 700 mastiya | WS |  | 300000 | Divisional secretary office |  |  |  | 1
2 | Developing the naturs beach road in mastiya | kaluthara | kaluthara | 700 mastiya | RA |  | 500000 | Divisional secretary office |  |  |  | 1
3 | Developing the temple road in mastiya | kaluthara | kaluthara | 700 mastiya | RA |  | 500000 | Divisional secretary office |  |  |  | 1
4 | Developing the baduwatta road in kawatayagoda | kaluthara | kaluthara | 701 mahagonaduwa | RA | 247 | 920000 | Divisional secretary office | Gamunu govi sanwidanaya | [11 empty] | 1 | 15
5 | Developing the ellanthuduwa road in kawatayagoda | kaluthara | kaluthara | 701 mahagonaduwa | RA |  | 1000000 | Divisional secretary office |  |  |  | 1
6 | supplying water line to the by road kawatayagoda palawatta | kaluthara | kaluthara | 701 mahagonaduwa | WS |  | 250000 | Divisional secretary office |  |  |  | 1
7 | Developing the thalhenathuduwa road in kudagonaduwa & by road of temple | kaluthara | kaluthara | 701 a kudagonaduwa | RA | 328 | 1000000 | Divisional secretary office | Gamunu govi sanwidanaya | [7 empty] | 1 |  |  |  |  | 300
8 | Developing the by road in nilupuluyana | kaluthara | kaluthara | 701 a kudagonaduwa | RA |  | 500000 | Divisional secretary office |  |  |  | 1
9 | Developing the temple road in kudagonaduwa | kaluthara | kaluthara | 701 a kudagonaduwa | RA |  | 500000 | Divisional secretary office |  |  |  | 1
10 | Developing the main road in kandaudawatta | kaluthara | kaluthara | 703 malagama north | RA |  | 1000000 | Divisional secretary office |  |  |  | 1
11 | Developing the sirimalwatta road | kaluthara | kaluthara | 703 a habaralagahalanda | RA | 160 | 1000000 | Divisional secretary office | kondaswatta suba sadaka samithiya | [7 empty] | 1 |  |  |  |  | 19
12 | Developing the namal uyana road | kaluthara | kaluthara | 703 b malagama south | RA | 110 | 500000 | Divisional secretary office | kondaswatta suba sadaka samithiya | [7 empty] | 1 |  |  |  |  | 25
13 | Developing the upasikarama 1 st lane | kaluthara | kaluthara | 703 b malagama south | RA | 76 | 500000 | Divisional secretary office |  |  |  |  | 1 | [8 empty] | 7
14 | Developing the temple road 1 st lane | kaluthara | kaluthara | 703 b malagama south | RA | 60 | 500000 | Divisional secretary office |  |  |  |  | 1 | [8 empty] | 25
15 | Re-build roofing in sithum sewana budu madura | kaluthara | kaluthara | 705 maharakma | RC |  | 800000 | Divisional secretary office |  |  |  | 1
16 | Developing the 2 nd lane of galagawela road | kaluthara | kaluthara | 705 maharakma | RA | 94.51 | 950000 | Divisional secretary office | chamlipura kantha grama sanwardana samithiya | 914000 | [10 empty] | 1 | 55
17 | supplying water line on the mahagedarawatta road | kaluthara | kaluthara | 705 a mawala south | WS |  | 200000 | Divisional secretary office |  |  |  | 1
18 | Developing the mahawatta road in mawala | kaluthara | kaluthara | 705 b mawala | RA | 214 | 1000000 | Divisional secretary office |  |  |  |  | 1
19 | Developing near the dalkade road in mawala | kaluthara | kaluthara | 705 b mawala | RA | 70 | 500000 | Divisional secretary office |  |  |  |  | 1
20 | Developing the thotupalawatta road in moronthuduwa | kaluthara | kaluthara | 706 moronthuduwa north | RA |  | 1000000
21 | Developing the sathbudu vihara road | kaluthara | kaluthara | 707 moronthuduwa north | RA |  | 800000
22 | Developing the bikku hostal in moronthuduwa sri maha bodi viharaya | kaluthara | kaluthara | 708 moronthuduwa north | RC |  | 500000
23 | Developing the bohawatta road | kaluthara | kaluthara | 706 a nanduwa | RC |  | 1260000
24 | Repairaing the sri suarmarama temple's darmasala building in moronthuduwa | kaluthara | kaluthara | 707 a nanduwa | RC |  | 400000
25 | Developing the 5 th lane of batahena road in mornthuduwa | kaluthara | kaluthara | 706 b moronthuduwa south | RA |  | 1000000
26 | Developing the nilketha 4 th lane of tharuna sewa mawatha | kaluthara | kaluthara | 707 b moronthuduwa south | RA |  | 500000
27 | Developing the nilketha 2 nd lane of tharuna sewa mawatha | kaluthara | kaluthara | 708 b moronthuduwa south | RA |  | 500000
28 | Developing the nilketha 1 st lane of gunasekarawatta in moronthuduwa | kaluthara | kaluthara | 709 b moronthuduwa south | RA |  | 1000000
29 | supplying water line to the maragahawatta road | kaluthara | kaluthara | 710 b moronthuduwa south | WS |  | 500000
30 | Developing the sri saddathissa road 0f saranatissa road | kaluthara | kaluthara | 707 pohaddara mulla east | RA |  | 1000000
31
Total
* Projects should be categorized for following sectors | [6 empty] | ** Physical progress
a |  |  |  | Circular Code
RA- Rural Access |  |  |  | 2 | 3 |  | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  |  | 9 |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
SF- Sanitory Facility |  |  |  | 4 |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
PG- Play Ground |  |  |  | 5 |  |  | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  |  | 1 |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  |  | 7 |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
RC- Religious Center Development |  |  |  | 10 |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
SW- Social Welfare |  |  |  | 8 |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
HD- Housing Development |  |  |  | 12
SE- Sola Electricity |  |  |  | 11
WS- Rural Water Supply (Drinking water) |  |  |  | 6
OI- Other infastructure |  |  |  | 6

## all
Gamperaliya- Rapid Rural Development Programme - 2019
Physical and Financial Progress of the Month of June 2019
District : KALUTHRA
No | Name of the Project | Electorate | DS Division | GN Division |  | Approved Amount (Rs, Mn.) | Name of the Contractor/ Society | Progress
[5 empty] | Sector |  |  | Financial |  | Physical **
[8 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[11 empty] | B1 | B2 | B3 | B4
1 | Development of Nature's Beach Road | Kaluthara | kaluthara | 700 mastiya | RA | 2000000 | Mastia 02 Water Society | 1940000 | [10 empty] | 1
2 | Development of Kudayagoda Baduwattha road | Kaluthara | kaluthara | 701 mahagonaduwa | RA | 920000 | Gemunu Farmers' Society | 884362 | [10 empty] | 1
3 | Development of Kalthiyagoda Hallston Road | Kaluthara | kaluthara |  | RA | 1130000 | Gemunu Farmers' Society | 1079666 | [10 empty] | 1
4 | Developing the by-pass through Thalahentuduwa road in Kudagonaduwa and through it to the temple | Kaluthara | kaluthara | 701 a kudagonaduwa | RA | 1000000 | Gemunu Farmers' Society | 970000 | [10 empty] | 1
5 | Development of Nilupul Uyana Road | Kaluthara | kaluthara | 701 a kudagonaduwa | RA | 600000 | Gemunu Farmers' Society | [11 empty] | 1
6 | Development of Kudagonduwa temple road | Kaluthara | kaluthara | 701 a kudagonaduwa | RA | 600000 | Gemunu Farmers' Society | 582000 | [10 empty] | 1
7 | Development of Kanda Udawatta Announcer Estate Road | Kaluthara | kaluthara | 703 malagama north | RA | 1000000 | Kongaswatta Welfare Society | [11 empty] | 1
8 | Development of Sirimalwatta road | Kaluthara | kaluthara | 703 a habaralagahalanda | RA | 1000000 | Kongaswatta Welfare Society | 966542 | [10 empty] | 1
9 | Development of Sirimalwatta road 2 stage | Kaluthara | kaluthara | 703 a habaralagahalanda | RA | 310000 |  |  |  |  | 1
10 | Development of Namal Uyana road | Kaluthara | kaluthara | 703 b malagama south | RA | 500000 | Kongaswatta Welfare Society | 477333 | [10 empty] | 1
11 | Development of Namal Uyana road-2 stage | Kaluthara | kaluthara | 704 b malagama south | RA | 165000 |  |  |  |  | 1
12 | Development of 1st lane upasiakaram | Kaluthara | kaluthara | 703 b malagama south | RA | 400000 | [12 empty] | 1
13 | Development of the temple road 1 lane | Kaluthara | kaluthara | 703 b malagama south | RA | 500000 | [12 empty] | 1
14 | The 2nd Lane of Galagawela Road | Kaluthara | kaluthara | 705 maharakma | RA | 950000 | chamlipura kantha grama sanwardana | 914380 | [10 empty] | 1
15 | Development of the mawala mahawtta road | Kaluthara | kaluthara | 705 b mawala | RA | 1000000 | Maawala Sripushudhadhama Temple Senior Citizens Organization | 970000 | [10 empty] | 1
16 | Development of the mawala dalkade road | Kaluthara | kaluthara | 705 b mawala | RA | 500000 | Maawala Sripushudhadhama Temple Senior Citizens Organization | 485000 | [10 empty] | 1
17 | Development of the mawala dalkade road- 2 stage | Kaluthara | kaluthara | 705 b mawala | RA | 100000 |  |  |  |  | 1
18 | Development of bog watta road | Kaluthara | kaluthara | 706 a nanduwa | RA | 1020000 | Prathibha Youth Society | 963633.1 | [10 empty] | 1
19 | Development of Merynthuduwa Batahena 5th lane | Kaluthara | kaluthara | 706 b moronthuduwa south | RA | 1000000 | Malagama Eksity Welfare Society | 970000 | [10 empty] | 1
20 | Development of Mawathawa Mawatha, Nilketha 2nd Lane | Kaluthara | kaluthara | 706 b moronthuduwa south | RA | 500000 | Mahalanda United Funeral aids Society | 485000 | [10 empty] | 1
21 | Development of the road from Moronthuduwa to Sathubudu Vihara Mawatha to Kurunduwatta, Maharakrama road | Kaluthara | kaluthara | 706 b moronthuduwa south | RA | 2000000 |  |  |  |  | 1
22 | Development of tharunasewa Mawatha, 11 Lane | Kaluthara | kaluthara | 706 b moronthuduwa south | RA | 630000 | Mahalanda United Funeral aids Society | [8 empty] | 1
23 | Development of Sri Saddamathissa Mawatha in Saranathissa Mawatha | Kaluthara | kaluthara | 707 pohaddaramulla east | RA | 920000 | Senior Citizens' Elderly Society | 911800 | [10 empty] | 1
24 | Development of the koladada road | Kaluthara | kaluthara | 707 pohaddaramulla east | RA | 1500000 |  |  |  | 1
25 | Developing a stone to the left of the road from the coastal road to the left of the stone road | Kaluthara | kaluthara | 707 pohaddaramulla west | RA | 500000 | Senior Citizens' Elderly Society | [11 empty] | 1
26 | Developing the rest of the hotel from Wendool Hotel to middle road (towards Wadduwa) | Kaluthara | kaluthara | 707 pohaddaramulla west | RA | 500000 | Senior Citizens' Elderly Society | [10 empty] | 1
27 | Development of Pothupitiya Panapitiya Road 3rd cross road (opposite the Sri Dharmathilkarama Road) | Kaluthara | kaluthara | 708 pothupitiya north | RA | 500000 | Korosduwa Solid Water Park Watta Welanda Society | 485000 | [10 empty] | 1
28 | Cross Road development at Pothupitiya Round Road (Dayananda Wijesena's Home Road) | Kaluthara | kaluthara | 708 pothupitiya north | RA | 500000 | Unity Welfare Society | 485000 | [10 empty] | 1
29 | Cross Road development at Pothupitiya Round Road (Dayananda Wijesena's Home Road)-2 stage | Kaluthara | kaluthara | 708 pothupitiya north | RA | 500000 |  |  |  |  | 1
30 | Development of Pothupitiya Panapitiya Road 3rd cross road- 2 stage | Kaluthara | kaluthara | 708 pothupitiya north | RA | 870000 | Korosduwa Solid Water Park Watta Welanda Society | 827542.48 | [10 empty] | 1
31 | School road development road(podinilamege niwasa para) | Kaluthara | kaluthara | 708 pothupitiya north | RA | 170000 | United Victory Society | 164900 | [10 empty] | 1
32 | Development of 31 Waththa colony road (Nikapitiya Bandara Road) | Kaluthara | kaluthara | 708 a pothupitiya south | RA | 1000000 | Ethanord is a United Buddhist and a public service | 970000 | [10 empty] | 1
33 | Development of 31 Waththa colony road (Nikapitiya Bandara Road)- 2 stage | Kaluthara | kaluthara | 708 a pothupitiya south | RA | 550000 |  |  |  |  | 1
34 | The rest of the Katuwangoda Road up to Pallama | Kaluthara | kaluthara | 708 b pothupitiya east | RA | 1000000 | The United Victim Associaction Society, Goldwee | 970000 | [10 empty] | 1
35 | Develop the 4th Cross road in the Keroswiru Goldview Road | Kaluthara | kaluthara | 708 b pothupitiya east | RA | 520000 | The United Victim Associaction Society, Goldwee | 504400 | [10 empty] | 1
36 | Road development on Pelawatta road | Kaluthara | kaluthara | 708 b pothupitiya east | RA | 1160000 | The United Victim Associaction Society, Goldwee | 1125000 | [10 empty] | 1
37 | Development of Galle Road up to the road (Ariyaratne's house) | Kaluthara | kaluthara | 708 C pothupitiya west | RA | 300000 | The United Victim Associaction Society, Goldwee | [11 empty] | 1
38 | Lalith Indrapala's house development of the remaining part of the road (Tharbilin Kade road) | Kaluthara | kaluthara | 708 C pothupitiya west | RA | 350000 | The United Victim Associaction Society, Goldwee | [11 empty] | 1
39 | Cross Roads at Sugathadasa Road | Kaluthara | kaluthara | 708 C pothupitiya west | RA | 500000 | The United Victim Associaction Society, Goldwee | 485000 | [10 empty] | 1
40 | Development of Siyambalagaha road in Pothupitiya West (North) | Kaluthara | kaluthara | 708 C pothupitiya west | RA | 720000 | The United Victim Associaction Society, Goldwee | 698400 | [10 empty] | 1
41 | From Galle Road to Ranaviru Tudor Karunaratne Road | Kaluthara | kaluthara | 708 d madapothupitiya | RA | 1000000 | Randahadi Farmers' Organization | 970000 | [10 empty] | 1
42 | From Galle Road to Ranaviru Tudor Karunaratne Road -2 stage | Kaluthara | kaluthara | 708 d madapothupitiya | RA | 229000 | [12 empty] | 1
43 | From Galketiyagoda Road to Punchi Singhnon's House Road | Kaluthara | kaluthara | 708 d madapothupitiya | RA | 330000 | The United Victim Associaction Society, Goldwee | 320000 | [10 empty] | 1
44 | Development of the rest area at Gekatiyagoda Kajwatta Road | Kaluthara | kaluthara | 708 d madapothupitiya | RA | 255000 | The United Victim Associaction Society, Goldwee | [8 empty] | 1
45 | The first part of Kapilawela road and the final development | Kaluthara | kaluthara | 709 kalapugama east | RA | 800000 | Kalupagama Youth Society | 776000 | [10 empty] | 1
46 | Development of Kigakadawatta Road, Kajwaththa | Kaluthara | kaluthara | 709 kalapugama east | RA | 500000 | Kalupagama Youth Society | [11 empty] | 1
47 | Development of the remaining section of Deervuwa Parkway main street | Kaluthara | kaluthara | 709 a delduwa | RA | 750000 | Delduwa Elder's Society | [11 empty] | 1
48 | Development of Delduwa Ranmuthu Uyana buddhist road | Kaluthara | kaluthara | 709 a delduwa | RA | 1750000 | Delduwa Elder's Society | [11 empty] | 1
49 | Development of Fantasy Park Mandanthuva Road | Kaluthara | kaluthara | 709 b nugagoda | RA | 545000 | Nugagoda Senior Citizens' Association | [8 empty] | 1
50 | Development of Kithulgahathuduwa road | Kaluthara | kaluthara | 709 c kalapugama west | RA | 1000000 | Kalupagama Youth Society | [7 empty] | 1
51 | Road development of Kithulgahathuduwa Lal Kumara's Road | Kaluthara | kaluthara | 709 c kalapugama west | RA | 800000 | Kalupagama Youth Society | 776000 | [10 empty] | 1
52 | Development of the access road from the bank to the hill | Kaluthara | kaluthara | 709 d ariyagama | RA | 155000 | ariyagama Elder's Society | 150350 | [10 empty] | 1
53 | Development of 5th lane at Ariyagama | Kaluthara | kaluthara | 709 d ariyagama | RA | 500000 | ariyagama Elder's Society | 485000 | [10 empty] | 1
54 | Development of 5th lane at Ariyagama- 2 stage | Kaluthara | kaluthara | 710 d ariyagama | RA | 130000 |  |  |  |  | 1
55 | Expansion of the balance portion of the 3rd Floor of the Kepiwatta Road | Kaluthara | kaluthara | 709 d ariyagama | RA | 500000 | Kopiyawatta United Welfare Society | 485000 | [10 empty] | 1
56 | Development of the balance section of the road near Kudawaskaduwa Wediyawaththa Lasitha | Kaluthara | kaluthara | 710 kudawaskaduwa north | RA | 940000 | Mandakariwatta Community Society | 911800 | [10 empty] | 1
57 | Preparation of the road and the drainage system from Mr. Victor Wilton's house in Kandawatte Paya | Kaluthara | kaluthara | 710 kudawaskaduwa north | RA | 1000000 | Mandakariwatta Community Society | 970000 | [10 empty] | 1
58 | Development of High way Park City Road at Kobaduwa | Kaluthara | kaluthara | 710 a kudawaskaduwa south | RA | 650000 | Our own boyfriend's club | 615428 | [10 empty] | 1
59 | Development of road from development road | Kaluthara | kaluthara | 710 a kudawaskaduwa south | RA | 700000 | Our own boyfriend's club | 662412.65 | [10 empty] | 1
60 | Development of the opening road near Siribulugoda's Development Road | Kaluthara | kaluthara | 710 a kudawaskaduwa south | RA | 650000 | Our own boyfriend's club | 534291.2 | [10 empty] | 1
61 | From the house of Mrs. Nayana to the place of the residence of Senaratne, the rest of the road is being developed | Kaluthara | kaluthara | 710 b kudawaskaduwa west | RA | 375000 | Our own boyfriend's club | [6 empty] | 1
62 | Develop the rest of the "Ranaviru Pd Dayash" Thalwa Mawatha rest | Kaluthara | kaluthara | 710 kudawaskaduwa east | RA | 1000000 | Mandakariwatta Community Society | 970000 | [10 empty] | 1
63 | samagipura Meda Mawatha E. Development of the rest of the area from Gileenne's house | Kaluthara | kaluthara | 710 kudawaskaduwa east | RA | 500000 | Mandakariwatta Community Society | 485000 | [10 empty] | 1
64 | Development of Sri Samagipura, Mandakariwatta road | Kaluthara | kaluthara | 710 kudawaskaduwa east | RA | 500000 | Mandakariwatta Community Society | 485000 | [10 empty] | 1
65 | Development of the road near Manjula Weerakoon's house in Panapitiya on Kalutara Horana Road | Kaluthara | kaluthara | 711 panapitiya south | RA | 500000 | Rural Development | 485000 | [10 empty] | 1
66 | Development of the Lower Pradeshiya Mawatha from Fourmun junction Road in Rural Development Mawatha | Kaluthara | kaluthara | 711 a rannungala | RA | 500000 | Ranhungala Smart Sports Club | 485000 | [10 empty] | 1
67 | Development of an adjoining road to the Rural Development Road Cemetery | Kaluthara | kaluthara | 711 a rannungala | RA | 500000 | Ranhungala Smart Sports Club | 478650.08 | [10 empty] | 1
68 | Development of Panapitiya Hidiyawatta Mulle Gehesa road | Kaluthara | kaluthara | 711 panapitiya north | RA | 450000 | Panapitiya North Rural Development Association | 436500 | [10 empty] | 1
69 | Development of Panapitiya Technical College Road | Kaluthara | kaluthara | 711 panapitiya north | RA | 340000 | Panapitiya North Rural Development Association | 329800 | [10 empty] | 1
70 | Development of the road near petrol filling station at Panapitiya | Kaluthara | kaluthara | 711 panapitiya north | RA | 635000 | Panapitiya North Rural Development Association | [11 empty] | 1
71 | Development of old school watta road | Kaluthara | kaluthara | 711 panapitiya north | RA | 570000 | Panapitiya North Rural Development Association | [11 empty] | 1
72 | Development of Pitabadara road in Usgodalla Mawatha, Wijaya Mawatha | Kaluthara | kaluthara | 711 c usgodalla | RA | 1000000 | Prathibha Youth Society | [6 empty] | 1
73 | Development of sooriyapura main road | Kaluthara | kaluthara | 711 c usgodalla | RA | 500000 |  |  |  | 1
74 | Development of the road to Welanissam Mudalali's house | Kaluthara | kaluthara | 712 paraduwa | RA | 242000 | Diyagama Sudhikaramaya temple | 234740 | [10 empty] | 1
75 | Development of the Diyagama Gamegedawatte road | Kaluthara | kaluthara | 713 diyagama | RA | 500000 | Diyagama Sudhikaramaya temple | 485000 | [10 empty] | 1
76 | Construction of the culvert and the culvert along the river side of Diagampitiya Bogaha Junction | Kaluthara | kaluthara | 713 diyagama | RA | 430000 | Diyagama Dodamulla integrated farming organization | 417100 | [10 empty] | 1
77 | Development of Bulathgoda Estate | Kaluthara | kaluthara | 713 a dodammulla | RA | 1000000 | Diyagama Dodamulla integrated farming organization | 970000 | [10 empty] | 1
78 | Development of the na uyana road | Kaluthara | kaluthara | 714 mahawaskaduwa south | RA | 1000000 | Mahawaskaduwa Funeral and Social Service Society | 970000 | [10 empty] | 1
79 | Development of the na uyana road - 2 stage | Kaluthara | kaluthara | 714 mahawaskaduwa south | RA | 150000 |  |  |  |  | 1
80 | Development of the na uyana road - 3 stage | Kaluthara | kaluthara | 714 mahawaskaduwa south | RA | 230000 |  |  |  |  | 1
81 | Development of Guliyawaththa road | Kaluthara | kaluthara | 714 a mahawaskaduwa north | RA | 500000 | Mahawaskaduwa Funeral and Social Service Society | [8 empty] | 1
82 | Development of Shramadana mavatha | Kaluthara | kaluthara | 714 a mahawaskaduwa north | RA | 140000 | Mahawaskaduwa Funeral and Social Service Society | [6 empty] | 1
83 | Development of Ariyawatta Road at Kanda Temple Road | Kaluthara | kaluthara | 714 a mahawaskaduwa north | RA | 720000 | Mahawaskaduwa Funeral and Social Service Service Society | [11 empty] | 1
84 | Development of the road in front of the residence of Kanda Temple road | Kaluthara | kaluthara | 714 a mahawaskaduwa north | RA | 600000 | Mahawaskaduwa Funeral and Social Service Service Society | [11 empty] | 1
85 | Development of road near Mahawaskaduwa Munasinghe House | Kaluthara | kaluthara | 714 a mahawaskaduwa north | RA | 1690000 | Mahawaskaduwa Funeral and Social Service Service Society | [11 empty] | 1
86 | Develop the rest of the road on the Dediyawala road | Kaluthara | kaluthara | 715 dediyawala | RA | 1000000 | Dediyawala Rural Development Association | 970000 | [10 empty] | 1
87 | Development of the remaining part of Kanda road on 2nd floor-2 stage | Kaluthara | kaluthara | 715 dediyawala | RA | 130000 |  |  |  |  | 1
88 | Construction of Drainage System along the 11th Lane Road at Kandakuruduwaththa Road | Kaluthara | kaluthara | 715 dediyawala | RA | 1100000 |  |  |  | 1
89 | Development of Maduruwela Lenviyawatta Road | Kaluthara | kaluthara | 715 dediyawala | RA | 500000 | Dediyawala Rural Development Association | [6 empty] | 1
90 | Development of culverts and side drain points at Kandikudi Garden, 12th Lane. | Kaluthara | kaluthara | 715 dediyawala | RA | 600000 | Dediyawala Rural Development Association | [6 empty] | 1
91 | Development of Kandakuliya Garden at 8th Lane | Kaluthara | kaluthara | 715 dediyawala | RA | 900000 | Dediyawala Rural Development Association | [6 empty] | 1
92 | Development of Kandakuliya Garden at 14th Lane | Kaluthara | kaluthara | 715 dediyawala | RA | 500000 |  |  |  | 1
93 | onstruction of the balance on the side of the road on the side of the road that lies on Kapuheena Ruprapoda connecting line | Kaluthara | kaluthara | 715 a kapuhena | RA | 1000000 | [9 empty] | 1
94 | Construction of the remaining part of Kupukahena main road | Kaluthara | kaluthara | 715 a kapuhena | RA | 538000 |  |  |  |  | 1
95 | The final section of the Kudoduwegama Pravo Galgamuwa road | Kaluthara | kaluthara | 716 ugalbada east | RA | 1000000 | Peacebuild Cooperative Society | 970000 | [10 empty] | 1
96 | Development of road near Ananda Wijayasiri's house | Kaluthara | kaluthara | 716 a ugalbada west | RA | 1000000 | Peacebuild Cooperative Society | 970000 | [10 empty] | 1
97 | Development of road near Chaminda's residence | Kaluthara | kaluthara | 717 a ugalbada west | RA | 500000 | Peacebuild Cooperative Society | [11 empty] | 1
98 | evelopment of the first lane of the Nedungashena Kopiyawatta land | Kaluthara | kaluthara | 716 b vijerattnawatta | RA | 300000 | Peacebuild Cooperative Society | [11 empty] | 1
99 | Development of Nedungashenna main road | Kaluthara | kaluthara | 716 b vijerattnawatta | RA | 500000 | Peacebuild Cooperative Society | [6 empty] | 1
100 | Development of Malwatta National Road | Kaluthara | kaluthara | 716 b vijerattnawatta | RA | 455000 | Peacebuild Cooperative Society | 441350 | [10 empty] | 1
101 | Preparation of drainage system at the by road | Kaluthara | kaluthara | 717 kaluthara north | RA | 1300000 |  |  |  |  | 1
102 | Construction of the road and drainage to the right near Jayweera's residence | Kaluthara | kaluthara | 717 a desastra north | RA | 822000 | Janasahana Foundation and mutual aid society | [7 empty] | 1
103 | Development of Kalutara North Thisara garden | Kaluthara | kaluthara | 717 a desastra north | RA | 725000 | Janasahana Foundation and mutual aid society | 703250 | [10 empty] | 1
104 | Development of road from Mr. Karunaratne's residence to Upendra's house | Kaluthara | kaluthara | 717 b thotupala | RA | 720000 | Janasahana Foundation and mutual aid society | [11 empty] | 1
105 | Development of the road leading to Panarama Hotel (Portland Road) | Kaluthara | kaluthara | 717 b thotupala | RA | 630000 | Janasahana Foundation and mutual aid society | [6 empty] | 1
106 | Development of the first by-passing road (Lakmini's house road) past the railway crossing of South Sri Sumangala road | Kaluthara | kaluthara | 717 b thotupala | RA | 250000 | Janasahana Foundation and mutual aid society | [6 empty] | 1
107 | Road development of Kalutara North Palitha Pushpakumara Road | Kaluthara | kaluthara | 717 c vidyasara | RA | 900000 | Nigrodhara Elders' Society | 873000 | [10 empty] | 1
108 | Development of Ranaviru Emale Bandula Mw | Kaluthara | kaluthara | 717 d desathra west | RA | 770000 | Nigrodhara Elders' Society | 746900 | [10 empty] | 1
109 | Development of road to Sirinivasa Mawatha (road leading to Bandusiri Hewage) | Kaluthara | kaluthara | 717 d desathra west | RA | 500000 | Nigrodhara Elders' Society | [7 empty] | 1
110 | Preparation of drain from the Irrigation Engineer's office in Siriniwis Mawatha | Kaluthara | kaluthara | 717 d desathra west | RA | 500000 | Nigrodhara Elders' Society | [7 empty] | 1
111 | Preparation of the drain at the common well in front of Alabadawaththa Sumathipala Mawatha, Kalutara North | Kaluthara | kaluthara | 717 d desathra west | RA | 250000 | Nigrodhara Elders' Society | [7 empty] | 1
112 | Development of the rest of the Sanidadapura main road | Kaluthara | kaluthara | 718 ethanamadala | RA | 1000000 | 718 B Botnicwatta Rural Development Association | 970000 | [10 empty] | 1
113 | Development of Moragahakanda Estate, Ranaviru Ussan Randika Mawatha | Kaluthara | kaluthara | 718 ethanamadala | RA | 500000 | Ethanadala - Jawatte United Buddhist Social Service Society | 463472.3 | [10 empty] | 1
114 | Elaborate the first part of Pepper Hills Road at Ethanamadala Prison Road | Kaluthara | kaluthara | 718 ethanamadala | RA | 995000 | Ethanadala - Jawatte United Buddhist Social Service Society | 965150 | [10 empty] | 1
115 | Development of Cinnamon Road | Kaluthara | kaluthara | 718 a jawatta | RA | 1400000 | Suseela rural society | 1358000 | [10 empty] | 1
116 | Development of a byroad near the wood mill | Kaluthara | kaluthara | 718 b botnikwata | RA | 1000000 | 718 B Botnicwatta Rural Development Association | [11 empty] | 1
117 | Development of Ukuliyadeniya Waththa 2nd Lane | Kaluthara | kaluthara | 718 b botnikwata | RA | 1000000 | 719 B Botnicwatta Rural Development Association | 970000 | [10 empty] | 1
118 | Develop the rest of the Ikiliyadeniya Watta Mawatha main road | Kaluthara | kaluthara | 718 b botnikwata | RA | 354000 |  |  |  | 1
119 | Development of Delgahawattha road near Veeragoda Pushparama Road garage | Kaluthara | kaluthara | 718 c vilegoda north | RA | 1000000 | Wilegoda Suseela Rural Elders Society | 957667.42 | [10 empty] | 1
120 | Development of the Sirigama Delgahawaththa road | Kaluthara | kaluthara | 718 c vilegoda north | RA | 500000 | Wilegoda Suseela Rural Elders Society | 485000 | [10 empty] | 1
121 | Development of the middle section of the by-road at Wijerama Mawatha Amarapala's house | Kaluthara | kaluthara | 718 c vilegoda north | RA | 350000 | Wilegoda Suseela Rural Elders Society | 339500 | [10 empty] | 1
122 | Development of Sirilanda Prison Road | Kaluthara | kaluthara | 718 d malwatta | RA | 1000000 | Aruna Farmers Society | [11 empty] | 1
123 | Uggalbada 1st mile post road development | Kaluthara | kaluthara | 718 d malwatta | RA | 600000 | [7 empty] | 1
124 | Development of the Malwatta by road | Kaluthara | kaluthara | 718 d malwatta | RA | 852000 | Unity 93 Welfare Society | [11 empty] | 1
125 | Development of Kithulawa Damanawatta Road | Kaluthara | kaluthara | 723 kithulawa | RA | 400000 | Ekamuthu Public Service Welfare and Death Donation Society | [6 empty] | 1
126 | Developing new village on Mihikathawatta new village | Kaluthara | kaluthara | 723 kithulawa | RA | 500000 | Keththarama elders society | [11 empty] | 1
127 | Development of Mihikatha Watta Duwa road in Kitulawa | Kaluthara | kaluthara | 723 kithulawa | RA | 500000 | Keththarama elders society | [6 empty] | 1
128 | Development of the section of the Mihikatha Watta road in Kithulawa | Kaluthara | kaluthara | 723 kithulawa | RA | 1280000 | Ekamuthu Public Service Welfare and Death Donation Society | [11 empty] | 1
129 | Development of the road near Kithulawa Prabath's house | Kaluthara | kaluthara | 723 kithulawa | RA | 600000 | Keththarama elders society | [6 empty] | 1
130 | Development of the by road at Alviswatta Kurunda | Kaluthara | kaluthara | 723 a alwiswatta | RA | 600000 | [12 empty] | 1
131 | Development of the rest of the by road at Ruwan Keke | Kaluthara | kaluthara | 723 a alwiswatta | RA | 670000 | [12 empty] | 1
132 | Development of Circular road of Ilakwatta Samyn road | Kaluthara | kaluthara | 723 b ilukwatta | RA | 780000 | Unity 93 Welfare Society | 756600 | [10 empty] | 1
133 | Development of de-park Uyana road in Godaparagahahena road | Kaluthara | kaluthara | 723 c godaparagahahena | RA | 1200000 | People welfare Welfare Society | [11 empty] | 1
134 | Development of the 3 storied road in Paradise Road | Kaluthara | kaluthara | 723 c godaparagahahena | RA | 500000 | Godaparagahahena Suhada Senior Citizens' Association | [11 empty] | 1
135 | Development of the remaining road to Paradise Gate Grama Niladhari office (near Suranga's house) | Kaluthara | kaluthara | 723 c godaparagahahena | RA | 800000 | Godaparagahahena Suhada Senior Citizens' Association | 776000 | [10 empty] | 1
136 | Development of Lintanwatta Road | Kaluthara | kaluthara | 723 c godaparagahahena | RA | 890000 | PEOPLE Welfare Society | 863300 | [10 empty] | 1
137 | Development of Paradise Gate 3rd Avenue | Kaluthara | kaluthara | 723 c godaparagahahena | RA | 855000 |  |  |  | 1
138 | Development of Kanda Uda road near Munamalgahawatta well (Buddha statue) | Kaluthara | kaluthara | 723 d vilegoda south | RA | 400000 |  |  |  |  | 1
139 | Development of the rest of the 2nd cross road | Kaluthara | kaluthara | 723 d vilegoda south | RA | 500000 |  |  |  |  | 1
140 | Development of the road near Aluthpara Ranjith Wasantha, Polhota | Kaluthara | kaluthara | 723 e palathota | RA | 660000 | Farmers' organization | [6 empty] | 1
141 | Development of road to Walapakawaththa, Aluthpura, palathita | Kaluthara | kaluthara | 723 e palathota | RA | 583000 | Farmers' organization | 565510 | [10 empty] | 1
142 | Development of Aluthpara tappa Kotuwathawatta road | Kaluthara | kaluthara | 723 e palathota | RA | 540000 |  |  |  |  | 1
143 | Development of road from Malani Benjamin's house at Panvila Hillflower Road | Kaluthara | kaluthara | 723 f thekkawatta | RA | 1240000 |  |  |  |  | 1
144 | Development of the rest of Nilwethettawatte 1 lane at Panwila | Kaluthara | kaluthara | 723 f thekkawatta | RA | 600000 | Panvila Terrace Sports Club | 582000 | [10 empty] | 1
145 | Development of the road near Panvila Terrace Asela Arachchi | Kaluthara | kaluthara | 723 f thekkawatta | RA | 1000000 | Panvila Terrace Sports Club | 970000 | [10 empty] | 1
146 | Construction of the road near Panwila Terrace Nimal Perera | Kaluthara | kaluthara | 723 f thekkawatta | RA | 1000000 | Panvila Terrace Sports Club | 970000 | [10 empty] | 1
147 | Development of road from Panwila Nilketawaththa Suresh Prasanga's house | Kaluthara | kaluthara | 723 f thekkawatta | RA | 500000 | Panvila Terrace Sports Club | 485000 | [10 empty] | 1
148 | Development of road from Panwila Nilketawaththa Suresh Prasanga's house 2 stage | Kaluthara | kaluthara | 723 f thekkawatta | RA | 230000 | [6 empty] | 1
149 | Preparation of drainage system from Galle Road to Gnanodaya Mawatha to Gregory's Road | Kaluthara | kaluthara | 725 kaluthara south | RA | 1550000 |  |  |  |  | 1
150 | Development of access way to Wehtamakada Jumma mosque | Kaluthara | kaluthara | 725 a kaluthara south | RA | 775000 | Kalutara Multipurpose Co-operative Society | 723044.75 | [10 empty] | 1
151 | Development of road to Dharma Vijaya Piriven Road, Ruwan Jayaweera's house | Kaluthara | kaluthara | 725 b welapura | RA | 1000000 | Sri Postwarama Dharmavijaya Piriven Vihara Task Force Society | 819095.8 | [10 empty] | 1
152 | Development of the road to Deuwan's house on the right side of Soysa road | Kaluthara | kaluthara | 725 b welapura | RA | 1000000 | Sri Postwarama Dharmavijaya Piriven Vihara Task Force Society | 970000 | [10 empty] | 1
153 | Development of Dias Jayatilake Mawatha at Wickramasinghe Place | Kaluthara | kaluthara | 727 mahawatta | RA | 845000 |  |  |  |  | 1
154 | Developing the road to Mahailetangala, Hettikikanda Holiday House | Kaluthara | kaluthara | 727 a atawila | RA | 650000 |  |  |  |  | 1
155 | Development of Ishara Uyana 1, 7, Wanni Mawatha, 6th Mawatha, 5th Avenue, Mahihinthiyagala | Kaluthara | kaluthara | 727 a atawila | RA | 1000000 | Unity 93 Welfare Society | 970000 | [10 empty] | 1
156 | Development of Isuru Uyana 2 access road | Kaluthara | kaluthara | 727 a atawila | RA | 500000 | Unity 93 Welfare Society | 485000 | [10 empty] | 1
157 | Drain up the Marikkar main street from main culverts to the mosque | Kaluthara | kaluthara | 727 b kudaheentiyangala | RA | 380000 | pubudu govi sanvidanaya | 368600 | [10 empty] | 1
158 | Development of 6th lane of Marikkar Street | Kaluthara | kaluthara | 727 b kudaheentiyangala | RA | 780000 | pubudu govi sanvidanaya | [8 empty] | 1
159 | Construction of a side wall of a section of the Marikkar Street Canal | Kaluthara | kaluthara | 727 b kudaheentiyangala | RA | 1000000 | pubudu govi sanvidanaya | [6 empty] | 1
160 | Development of the Suhadala Road and the rest of it | Kaluthara | kaluthara | 727 c kuruduwatta | RA | 500000 | Kalutara Multipurpose Co-operative Society Ltd | 485000 | [10 empty] | 1
161 | Preparation of the drain in front of the Sesamearamaya temple | Kaluthara | kaluthara | 727 c kuruduwatta | RA | 500000 | Kalutara Multipurpose Co-operative Society Ltd | 485000 | [10 empty] | 1
162 | Development of road near Wijeyapala's house 2 nd Mawatha, Gemunu Mawatha, Mahahinettiyangala | Kaluthara | kaluthara | 727 d mahaheenatiyangala | RA | 1000000 | Unity 93 Welfare Society | 970000 | [10 empty] | 1
163 | Development of road near Wijeyapala's house 2 nd Mawatha, Gemunu Mawatha, Mahahinettiyangala - 2 stage | Kaluthara | kaluthara | 727 d mahaheenatiyangala | RA | 400000 |  |  |  |  | 1
164 | Development of drainage through Mahakiniyangala, Polwatte Kochchikotuwa | Kaluthara | kaluthara | 727 d mahaheenatiyangala | RA | 600000 |  |  |  |  | 1
165 | Development of Mr. Polwatte's house in Mahahinetiyangala | Kaluthara | kaluthara | 727 d mahaheenatiyangala | RA | 400000 |  |  |  |  | 1
166 | Em.bi. Construction of a drain in front of Eranga Banquet Hall | Kaluthara | kaluthara | 727 e akkaraoda | RA | 500000 | Kalutara Multipurpose Co-operative Society Ltd | [11 empty] | 1
167 | Development of drainage and drain near the Cooperative Cooperative | Kaluthara | kaluthara | 727 e akkaraoda | RA | 1000000 | Kalutara Multipurpose Co-operative Society Ltd | [11 empty] | 1
168 | Making the concrete drain on the main road Mahahineteengala Nimathhera Asapuwa | Kaluthara | kaluthara | 727 f wattamulla | RA | 1000000 | Unity 93 Welfare Society | 970000 | [10 empty] | 1
169 | Development of the 1st road in Mahahinetiyangala Mayura area | Kaluthara | kaluthara | 727 f wattamulla | RA | 500000 |  |  |  |  | 1
170 | Development of Emmel Park Housing Scheme 1st Stage | Kaluthara | kaluthara | 727 f wattamulla | RA | 2000000 | Mayura Place Welfare Society | 1940000 | [10 empty] | 1
171 | Emirates Park Housing Project 2nd phase | Kaluthara | kaluthara | 727 f wattamulla | RA | 2000000 | Dandiwala Kupukhena Welfare Society | 1940000 | [10 empty] | 1
172 | Development of Emmer Park Housing Scheme Stage III | Kaluthara | kaluthara | 727 f wattamulla | RA | 2000000 | Nimthera Asapuwa Welfare Society | 1940000 | [10 empty] | 1
173 | Emari Park Housing Project Road 4th stage | Kaluthara | kaluthara | 727 f wattamulla | RA | 2000000 | Unity 93 Welfare Society | 1940000 | [10 empty] | 1
174 | Emergency Park Road Development Road 5th stage | Kaluthara | kaluthara | 727 f wattamulla | RA | 500000 | Unity 93 Welfare Society | 485000 | [10 empty] | 1
175 | Development of the 01st Lane on Ethawalawatta | Kaluthara | kaluthara | 727 f wattamulla | RA | 500000 | Unity 93 Welfare Society | 485000 | [10 empty] | 1
176 | Development of Uda road at Gaya Watte | Kaluthara | kaluthara | 729 nagoda south | RA | 1000000 | sinha sena sanvidanaya | 970000 | [10 empty] | 1
177 | Development of the 03rd lane of the Community hall at Community hall, Namalgama | Kaluthara | kaluthara | 729 nagoda south | RA | 500000 |  |  |  |  | 1
178 | Nagoda Matugama Road. Construction of a culvert near the house of Dayananda Mallikarachchi | Kaluthara | kaluthara | 729 nagoda south | RA | 800000 |  |  |  | 1
179 | Development of the Katavilawaththa Wushu Madrassa up to the left | Kaluthara | kaluthara | 729 a alubogahalanda | RA | 450000 |  |  |  | 1
180 | Road development of Nishantha's house near Nagoda hospital | Kaluthara | kaluthara | 729 a alubogahalanda | RA | 500000 | [12 empty] | 1
181 | Development of Sri Pandithararama Temple Road - Stage 1 | Kaluthara | kaluthara | 729 a alubogahalanda | RA | 2000000 | [6 empty] | 1
182 | Development of Sri Paksharanaarama Temple Road - Phase II | Kaluthara | kaluthara | 729 a alubogahalanda | RA | 313000 | [6 empty] | 1
183 | Development of road at Good Junction near Food City | Kaluthara | kaluthara | 729 a alubogahalanda | RA | 500000 | Lion Corporal | [11 empty] | 1
184 | Development of drains to Sri Sudarshanaramaya from Excise office | Kaluthara | kaluthara | 729 b nagoda west | RA | 1700000 | Peradeniya Wijayaba Farmers' Organization | [7 empty] | 1
185 | Improve the road and drainage system to the official quarters of the District Secretariat | Kaluthara | kaluthara | 729 b nagoda west | RA | 1000000 |  |  |  | 1
186 | Development of the road from Minuritenna to Lagos estate | Kaluthara | kaluthara | 729 c pulartan | RA | 1000000 | Pularatanwatta United Welfare Society | [7 empty] | 1
187 | Concreting the road with the remaining part of the dilapidated mountain pass at Pullerton Estate, 1st lane, Nagoda Gnanasiha Nahimi Mawatha. | Kaluthara | kaluthara | 729 c pulartan | RA | 1500000 |  |  |  | 1
188 | Rev. Gnanasinghe's Stage of the 1st stage | Kaluthara | kaluthara | 729 c pulartan | RA | 2000000 | Pularatanwatta United Welfare Society | 1940000 | [10 empty] | 1
189 | 2nd stage development of Gnanasinghe Nayagam Mawatha | Kaluthara | kaluthara | 729 c pulartan | RA | 2000000 |  | 1940000 | [10 empty] | 1
190 | Development of Meerithenna 1 Lane | Kaluthara | kaluthara | 729 c pulartan | RA | 1530000 |  |  |  |  | 1
191 | Development of Gnanasinghe Nayagam Mawatha stage 3 | Kaluthara | kaluthara | 729 c pulartan | RA | 2000000 |  | 1940000 | [10 empty] | 1
192 | Rehabilitation of narrow streets of 1,2,3,4,5 | Kaluthara | kaluthara | 729 c pulartan | RA | 800000 |  | 776000 | [10 empty] | 1
193 | Rehabilitation of narrow streets of 2,3-2 stage | Kaluthara | kaluthara | 729 c pulartan | RA | 170000 |  |  |  |  | 1
194 | Development of Asiri Mawatha | Kaluthara | kaluthara | 729 d galassa | RA | 1115000 |  | 1076749.96 | [10 empty] | 1
195 | Development of the house of Mrs. Asiri Mawatha Dhanawathi's house | Kaluthara | kaluthara | 729 d galassa | RA | 500000 |  | 485000 | [10 empty] | 1
196 | Development of Kankanamatta road | Kaluthara | kaluthara | 729 d galassa | RA | 590000 |  | 572300 | [10 empty] | 1
197 | Development of the final section of Kosala Mawatha | Kaluthara | kaluthara | 729 d galassa | RA | 410000 |  | 397700 | [10 empty] | 1
198 | Development of Kajaduwawatte road at Nagoda Hospital hospital | Kaluthara | kaluthara | 729 e kajuduwawatta | RA | 2000000 |  | 1907522 | [10 empty] | 1
199 | evelopment of 1st Crossroads, Cinnamon Gardens, Colombo 2 | Kaluthara | kaluthara | 729 f uswatta | RA | 350000 |  | 339500 | [10 empty] | 1
200 | Development of Soaditharamaya Central Road (Rathnayake's main road) | Kaluthara | kaluthara | 729 f uswatta | RA | 1415000 |  |  |  |  | 1
201 | Development of the depot road | Kaluthara | kaluthara | 729 f uswatta | RA | 1175000 | [7 empty] | 1
202 | Development of road in front of the Kachcheriyawatta garden | Kaluthara | kaluthara | 729 f uswatta | RA | 555000 | [7 empty] | 1
203 | Preparation of the drainage section from Percy's Gara's shop to the Re-open shop | Kaluthara | kaluthara | 729 g rajawatta aluth kotasa | RA | 1000000 | [8 empty] | 1
204 | Preparation of drainage system from pond to canal | Kaluthara | kaluthara | 729 h rajawatta parana kotasa | RA | 1600000 | [8 empty] | 1
205 | Development of the road to Mr. wendasivi Watta's house | Kaluthara | kaluthara | 729 I weniwalkatiya | RA | 500000 |  | 485000 | [10 empty] | 1
206 | Development of the lower road up to Wenivalaketiya to Mahimulla | Kaluthara | kaluthara | 729 I weniwalkatiya | RA | 1841000 |  | 1787355.68 | [10 empty] | 1
207 | Development of road near Taprobane International School, Dharmarama Road | Kaluthara | kaluthara | 730 wettumakad | RA | 1000000 |  | 970000 | [10 empty] | 1
208 | Development of a by road at Lastchann, Katukurunda | Kaluthara | kaluthara | 730 wettumakad | RA | 500000 | [7 empty] | 1
209 | Development of St. Sebesithan Road 5th Lane Road | Kaluthara | kaluthara | 730 a kalapuwa | RA | 410000 | [8 empty] | 1
210 | Development of Kalamulla Navodya road | Kaluthara | kaluthara | 731 a kalamulla south | RA | 1000000 |  | 800072.4 | [10 empty] | 1
211 | Development of Kalamulla Navodya road 2nd stage | Kaluthara | kaluthara | 731 a kalamulla south | RA | 62000 | [7 empty] | 1
212 | Development of the 01st lane in Nagodawatte in front of the lane (2nd stage) | Kaluthara | kaluthara | 731kalamulla east | RA | 320000 | [12 empty] | 1
213 | Development of the 01st lane in Nagodawatte in front of the lane (3 stage) | Kaluthara | kaluthara | 731kalamulla east | RA | 422676.49 |  |  |  | 1
214 | Developed in front of the sathosa 1st Lane of Nagodawatta | Kaluthara | kaluthara | 731kalamulla east | RA | 500000 | [12 empty] | 1
215 | Development of the road from Sumith Prasanna's guest house behind the Devalaya Church and development of the byroad from Mrs. Shanika Pradeepani | Kaluthara | kaluthara | 731kalamulla north | RA | 500000 | [12 empty] | 1
216 | Development of the road behind the Devalaya Church - second stage | Kaluthara | kaluthara | 731kalamulla north | RA | 235000 |  |  |  |  | 1
217 | Development of road to the Kalamulla fisheries | Kaluthara | kaluthara | 731kalamulla north | RA | 500000 | [7 empty] | 1
218 | Developing Fisheries Housing Road- 2 stage | Kaluthara | kaluthara | 731kalamulla north | RA | 1820000 |  |  |  |  | 1
219 | Development of Fathima Road 2 stage | Kaluthara | kaluthara | 731kalamulla north | RA | 1200000 |  | 1143534.4 | [10 empty] | 1
220 | Development of Fathima Road | Kaluthara | kaluthara | 731kalamulla north | RA | 600000 |  | 582000 | [10 empty] | 1
221 | Development of the road near Lalith Nishantha's 1st Lane on Sudarshanarama Road | Kaluthara | kaluthara | 731kalamulla east | RA | 500000 |  | 485000 | [10 empty] | 1
222 | Development of 1st junction of Sudarshanarama road - 2nd stage | Kaluthara | kaluthara | 731kalamulla east | RA | 320000 |  |  |  |  | 1
223 | Road development from Gallepara to Chandnapala's house | Kaluthara | kaluthara | 731kalamulla east | RA | 410000 | nandana tapowana center | [6 empty] | 1
224 | Sri Sudu from Vaudugoda Priyantha's residence | Kaluthara | kaluthara | 732 athagama east | RA | 500000 | isuru welfair socity | [6 empty] | 1
225 | Preparation of the drainage system behind the Shanaramaya Temple- 2 adiyara | Kaluthara | kaluthara | 732 athagama east | RA | 750000 | isuru welfair socity | [6 empty] | 1
226 | Development of masal gunasekara road | Kaluthara | kaluthara | 732 athagama east | RA | 500000 | gramasakthi sanwardana samithiya | 485000 | [10 empty] | 1
227 | Construction of Drainage System from the front of the Sumanaramaya Temple to the Canal | Kaluthara | kaluthara | 732 athagama west | RA | 1500000 | athagama metta wadihity samithiya | [7 empty] | 1
228 | Development of the road from Saumyapala's house on the coastal road on the Jalathoda Mawatha | Kaluthara | kaluthara | 732 athagama west | RA | 1200000 | athagama metta wadihity samithiya | 1163906.8 | [10 empty] | 1
229 | Development of the road from Saumyapala's house on the coastal road on the Jalathoda Mawatha - 2 stage | Kaluthara | kaluthara | 732 athagama west | RA | 225000 | athagama metta wadihity samithiya | 148314 | [10 empty] | 1
230 | Provision of Solar Power Facilities to Nugagoda Nagarakkarmarama temple | Kaluthara | kaluthara | 709 b nugagoda | RC | 500000 |  |  |  |  | 1
231 | Development of the bhikkhu hostel at Sri mahabodi temple in Moronthuduwa | Kaluthara | kaluthara | 706 moronthuduwa | RC | 500000 | [7 empty] | 1
232 | Repairing the Dharma Hall at Sri Sudharmarama Temple | Kaluthara | kaluthara | 706 a nanduwa | RC | 400000 | [10 empty] | 1
233 | Construction of the Daham School Building from the Moronthuduwa Sabbuduwa Viharaya | Kaluthara | kaluthara | 706 b moronthuduwa south | RC | 500000 |  |  |  | 1
234 | Completion of the Dhamma School building at Mahigajanarama Vihara | Kaluthara | kaluthara | 707 pohaddaramulla west | RC | 500000 |  |  |  |  | 1
235 | Completed the construction of the pavilion which is being constructed at the Sri indrajothtiyarama Viharaya | Kaluthara | kaluthara | 712 paraduwa | RC | 500000 | paraduwa govi sanvidanaya | [6 empty] | 1
236 | Completion of the pavilion constructed at Sri Sudharma Dharmashala Viharaya | Kaluthara | kaluthara | 714 mahawaskaduwa north | RC | 500000 |  |  |  |  | 1
237 | Conducting development works of the Malasna Rajamaha Viharaya | Kaluthara | kaluthara | 716 ugalbada east | RC | 500000 | [6 empty] | 1
238 | Development of St. John's Church | Kaluthara | kaluthara | 717 b thotupala | RC | 300000 | jana sahana padanama @ | [6 empty] | 1
239 | Completion of the Bodhirukkarama Dhamma school Building | Kaluthara | kaluthara | 718 a jawatta | RC | 500000 |  |  |  |  | 1
240 | Completion of the Siri Sariyutha Dhamma School at Sri Padmanarama Temple | Kaluthara | kaluthara | 723 d vilegoda south | RC | 500000 | padmarama vihara sanwardana samithiya | [6 empty] | 1
241 | Completion of the remaining building in the Alawiya mosque | Kaluthara | kaluthara | 727 e akkaraoda | RC | 800000 |  |  |  |  | 1
242 | Stage 1 of the construction of the holy Miycheal Dhamma School Building | Kaluthara | kaluthara | 729 b nagoda west | RC | 400000 |  |  |  |  | 1
243 | Reconstruction of the Dhamma school building at Sri Jayawardenalaramaya Bhikku Sanctuary. Stage 1 | Kaluthara | kaluthara | 729 b nagoda west | RC | 1000000 | [6 empty] | 1
244 | Construction of toilets system for Shailarama Dhamma School | Kaluthara | kaluthara | 729 e kajuduwawatta | RC | 300000 | [12 empty] | 1
245 | Development of Kataragama devalaya at Katukurunda | Kaluthara | kaluthara | 730 b katukurunda | RC | 500000 |  |  |  |  | 1
246 | Remaining part of the Dharmasalawa Viharaya at Atthagama Nandana thapovana | Kaluthara | kaluthara | 732 athagama east | RC | 500000 | [11 empty] | 1
247 | Development of bikkhu Nikethanaramaya | Kaluthara | kaluthara | 729 c pulartan | RC | 200000 |  |  |  |  | 1
248 | Development of Shakyasinghe Viharaya | Kaluthara | kaluthara | 729 I weniwalkatiya | RC | 200000 |  |  |  |  | 1
249 | Development of Jayawardenarama Viharaya | Kaluthara | kaluthara | 731 kalamulla east | RC | 200000 |  |  |  |  | 1
250 | Development of Kettharama Viharaya | Kaluthara | kaluthara | 727 mahawatta | RC | 200000 |  |  |  |  | 1
251 | Development of Sri Sudarshanarama Viharaya | Kaluthara | kaluthara | 729 a alubogahalanda | RC | 200000 |  |  |  |  | 1
252 | Development of Siri Sadaham Viharaya | Kaluthara | kaluthara | 729 I weniwalkatiya | RC | 300000 |  |  |  |  | 1
253 | Development of the Mahimulla Sri Lankarama Viharaya | Kaluthara | kaluthara |  | RC | 200000 |  |  |  |  | 1
254 | Development of Uttarachetiyarama Viharaya | Kaluthara | kaluthara | 701 a kudagonaduwa | RC | 200000 | [7 empty] | 1
255 | Development of the mosque , Saaviya | Kaluthara | kaluthara | 730 wettumakad | RC | 114000 | [6 empty] | 1
256 | Solar power facilities for Ganewatta Purana Viharaya | Kaluthara | kaluthara |  | RC | 500000 | [7 empty] | 1
257 | Providing drinking water to Delgahawaththa Road | Kaluthara | kaluthara | 700 mastiya | WS | 520469.3 |  |  |  |  | 1
258 | Supplying drinking water to the by-road on the Kawatayagoda Pelawatta road | Kaluthara | kaluthara | 701 mahagonaduwa | WS | 136629.5 |  |  |  |  | 1
259 | Supplying drinking water to Mahagerawatta road upto | Kaluthara | kaluthara | 705 a mawala south | WS | 143036.1 |  |  |  |  | 1
260 | Supply drinking water to Maragahawatta Road | Kaluthara | kaluthara | 706 b moronthuduwa south | WS | 172926.7 |  |  |  |  | 1
261 | Providing drinking water to Delduwa Navinna road | Kaluthara | kaluthara | 709 a delduwa | WS | 1246001.3 |  |  |  |  | 1
262 | Completion of the supply of water for the Kalogoda polkanda dam | Kaluthara | kaluthara | 711 panapitiya south | WS | 549496.76 | [6 empty] | 1
263 | Providing of drinking water from Gunagoda to Kalapugama border | Kaluthara | kaluthara | 712 paraduwa | WS | 446659.5 |  |  |  |  | 1
264 | Providing drinking water for near road at Dediyawala clinic | Kaluthara | kaluthara | 715 dediyawala | WS | 406922.1 |  |  |  |  | 1
265 | Supplying drinking water to the area at Dodammulla mada para, Diyagama | Kaluthara | kaluthara | 713 a dodammulla | WS | 946461.85 |  |  |  |  | 1
266 | Providing drinking water to the road behind the Pushparama Temple in Veyangoda | Kaluthara | kaluthara | 718 c vilegoda north | WS | 260579.7 |  |  |  |  | 1
267 | Supplying drinking water to lintanwatta sewa piyasa | Kaluthara | kaluthara | 723 c godaparagahahena | WS | 25000
268 | Supplying drinking water to Richmondcort Estate, Panwila | Kaluthara | kaluthara | 723 f thekkawatta | WS | 470339.2 |  |  |  |  | 1
269 | Providing drinking water facilities for the village of Tekawatta, Minuwan Udumulla | Kaluthara | kaluthara | 723 f thekkawatta | WS | 952801.5 |  |  |  |  | 1
270 | Development of the rest of the work at the Kalugama Junior School and the play ground | Kaluthara | kaluthara | 709 c kalapugama west | PG | 1200000 |  |  |  |  | 1
271 | Diyagama Maha Vidyalaya construction of a protective net around the playground | Kaluthara | kaluthara | 713 a dodammulla | PG | 1200000 | [9 empty] | 1
272 | Reconstruction of a playground for the Samanala playground | Kaluthara | kaluthara | 727 c kuruduwatta | PG | 1500000 |  |  |  |  | 1
273 | Preparation of Gamassha De Silva Ground | Kaluthara | kaluthara | 729 e kajuduwawatta | PG | 1000000 | [7 empty] | 1
274 | Reconstruction and renovation of the Pakistan Kondapitiya playground | Kaluthara | kaluthara | 730 wettumakad | PG | 500000 | [12 empty] | 1
275 | Development of Kalamulla playground | Kaluthara | kaluthara | 731 a kalamulla south | PG | 650000 | nanda | 630500 | [10 empty] | 1
276 | Construction of Children's Parks at Moronthuduwa, Kalapagama | Kaluthara | kaluthara | 709 c kalapugama west | PG | 1800000 |  |  |  | 1
277 | Construction of a toilets system at Musaeus College | Kaluthara | kaluthara | 731 a kalamulla south | SF | 400000 | [7 empty] | 1
278 | Reconstruction of toilets at the Roman Catholic College, Kalmulla | Kaluthara | kaluthara | 718 a jawatta | SF | 300000 |  |  |  |  | 1
279 | ND Mr. Neil Gamini | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  | 75000 |  |  |  |  | 1
280 | SA Mr. Athula Priyantha | Kaluthara | kaluthara | 729d galassa | HD | 150000 |  | 75000 |  |  |  |  | 1
281 | Mrs. Sunila Anoma Ranjani | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
282 | Mr. R. Sasath Silva | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
283 | Ṭi.ḍi. Ms. Chalonona died | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
284 | Mr. B. Sarath Silva | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
285 | Mr.k.m.p. Mendis | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  | 75000 |  |  |  |  | 1
286 | W. Mrs. Gunawathie | Kaluthara | kaluthara | 729 d galassa | HD | 150000 | [6 empty] | 1
287 | Kē.kē.ē.bī. Mr. Adikaram | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
288 | Ē.ē.si.ḍi. Mr. Priyankara | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
289 | Ār.ḍi.ḍi. Mrs. Sandamali | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  |  |  | 1
290 | Mr. Wally Vitharana | Kaluthara | kaluthara | 729 d galassa | HD | 150000 |  | 75000 |  |  |  |  | 1
291 | Mrs. PU Mushushani | Kaluthara | kaluthara | 729 Kaduwuwatte | HD | 150000 |  |  |  | 1
292 | Mrs. MADevika Kumari | Kaluthara | kaluthara | 729 Kaduwuwatte | HD | 150000 | [6 empty] | 1
293 | Mrs. P. Samanthi Perera | Kaluthara | kaluthara | 729 Kaduwuwatte | HD | 150000 |  |  |  | 1
294 | Mrs. WAI Kusumalatha | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  |  |  | 1
295 | Mrs. A.A Gunawathi | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  | 75000 |  |  |  |  | 1
296 | L.Dayani prithika | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 | [6 empty] | 1
297 | Mr. W.A.A.Kumarasinghe | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  | 75000 |  |  |  |  | 1
298 | Mr. W.D.rusantha. | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  |  |  | 1
299 | Mrs. PVW Premawathie | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  |  |  | 1
300 | Mr. MKJayit | Kaluthara | kaluthara | 729 Veniwalaketiya | HD | 150000 |  |  |  | 1
301 | Ms. D.Kamala Nandani | Kaluthara | kaluthara | 729 Nagoda South | HD | 150000 |  | 75000 |  |  |  |  | 1
302 | Mr. EA Sirisena Ajith | Kaluthara | kaluthara | 705 maharakma | HD | 150000 |  | 75000 |  |  |  |  | 1 |  |  |  | 1
303 | Mrs. D.D.G.Kumari perera | Kaluthara | kaluthara | 700 Mastia | HD | 150000 |  | 75000 |  |  |  |  | 1
304 | Mr. I.premarathna | Kaluthara | kaluthara | 700 Mastia | HD | 150000 |  |  |  | 1
305 | KB Ananda Perera | Kaluthara | kaluthara | 700 Mastia | HD | 300000 | [6 empty] | 1
306 | Mrs. K.nisanthanthi Surangika | Kaluthara | kaluthara | 700 Mastia | HD | 150000 | [6 empty] | 1
307 | Mrs. Hemawathi Jayasekara | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 | [6 empty] | 1
308 | M. Ms. Sumanawathie | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 |  | 75000 |  |  |  |  | 1
309 | Jessica Benjamin | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 |  | 75000 |  |  |  |  | 1
310 | Mr. KGS Gunarathna | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 | [6 empty] | 1
311 | Ms. K.Nanali Perera | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 |  | 75000 |  |  |  |  | 1
312 | Mrs. Shyamali Dilhani | Kaluthara | kaluthara | 723, F teakwatta | HD | 150000 | [6 empty] | 1
313 | Nuwan Thushara de Alwis | Kaluthara | kaluthara | 723E palathota | HD | 150000 |  | 75000 |  |  |  |  | 1
314 | H.Cherpala promoter | Kaluthara | kaluthara | 701 a gonaduwa | HD | 300000 |  |  |  | 1
315 | Mrs. K. Niina Nirosha | Kaluthara | kaluthara | 718 Ethanamal | HD | 150000 | [6 empty] | 1
316 | H.a.m.c...perērā | Kaluthara | kaluthara | 718 a Jawatte | HD | 150000 | [6 empty] | 1
[6 empty] | 206920000 |  | 90330926.02 |  | 28 | 58 | 0 | 30 | 31 | 11 | 7 | 2 | 2 | 147 | 316
* Projects should be categorized for following sectors | [5 empty] | ** Physical progress
a |  |  |  | Circular Code
RA- Rural Access |  |  |  | 2 | 3 | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  |  | 9 |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
SF- Sanitory Facility |  |  |  | 4 |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
PG- Play Ground |  |  |  | 5 |  | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  |  | 1 |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  |  | 7 |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
RC- Religious Center Development |  |  |  | 10 |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
SW- Social Welfare |  |  |  | 8 |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
HD- Housing Development |  |  |  | 12
SE- Sola Electricity |  |  |  | 11
WS- Rural Water Supply (Drinking water) |  |  |  | 6
OI- Other infastructure |  |  |  | 6

## RC
Gamperaliya- Rapid Rural Development Programme - 2019 | [16 empty] | Annexure D
Physical and Financial Progress of the Month of may 2019
District : KALUTHRA
No | Name of the Project | Electorate | DS Division | GN Division |  | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [12 empty] | No. of Beneficiaries | Remarks
[5 empty] | Sector |  |  |  |  | Financial |  | Physical **
[10 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
230 | Provision of Solar Power Facilities to Nugagoda Nagarakkarmarama temple | Kaluthara | kaluthara | 709 b nugagoda | RC |  | 500000 | [5 empty] | 1
231 | Development of the bhikkhu hostel at Sri mahabodi temple in Moronthuduwa | Kaluthara | kaluthara | 706 moronthuduwa | RC |  | 500000 | [8 empty] | 1
232 | Repairing the Dharma Hall at Sri Sudharmarama Temple | Kaluthara | kaluthara | 706 a nanduwa | RC |  | 400000 | [11 empty] | 1
233 | Construction of the Daham School Building from the Moronthuduwa Sabbuduwa Viharaya | Kaluthara | kaluthara | 706 b moronthuduwa south | RC |  | 500000 |  |  |  |  | 1
234 | Completion of the Dhamma School building at Mahigajanarama Vihara | Kaluthara | kaluthara | 707 pohaddaramulla west | RC |  | 500000 | [5 empty] | 1
235 | Completed the construction of the pavilion which is being constructed at the Sri indrajothtiyarama Viharaya | Kaluthara | kaluthara | 712 paraduwa | RC |  | 500000 |  | paraduwa govi sanvidanaya | [6 empty] | 1
236 | Completion of the pavilion constructed at Sri Sudharma Dharmashala Viharaya | Kaluthara | kaluthara | 714 mahawaskaduwa north | RC |  | 500000 | [5 empty] | 1
237 | Conducting development works of the Malasna Rajamaha Viharaya | Kaluthara | kaluthara | 716 ugalbada east | RC |  | 500000 | [7 empty] | 1
238 | Development of St. John's Church | Kaluthara | kaluthara | 717 b thotupala | RC |  | 300000 |  | jana sahana padanama @ | [6 empty] | 1
239 | Completion of the Bodhirukkarama Dhamma school Building | Kaluthara | kaluthara | 718 a jawatta | RC |  | 500000 | [5 empty] | 1
240 | Completion of the Siri Sariyutha Dhamma School at Sri Padmanarama Temple | Kaluthara | kaluthara | 723 d vilegoda south | RC |  | 500000 |  | padmarama vihara sanwardana samithiya | [6 empty] | 1
241 | Completion of the remaining building in the Alawiya mosque | Kaluthara | kaluthara | 727 e akkaraoda | RC |  | 800000 | [5 empty] | 1
242 | Stage 1 of the construction of the holy Miycheal Dhamma School Building | Kaluthara | kaluthara | 729 b nagoda west | RC |  | 400000 | [5 empty] | 1
243 | Reconstruction of the Dhamma school building at Sri Jayawardenalaramaya Bhikku Sanctuary. Stage 1 | Kaluthara | kaluthara | 729 b nagoda west | RC |  | 1000000 | [7 empty] | 1
244 | Construction of toilets system for Shailarama Dhamma School | Kaluthara | kaluthara | 729 e kajuduwawatta | RC |  | 300000 | [13 empty] | 1
245 | Development of Kataragama devalaya at Katukurunda | Kaluthara | kaluthara | 730 b katukurunda | RC |  | 500000 | [5 empty] | 1
246 | Remaining part of the Dharmasalawa Viharaya at Atthagama Nandana thapovana | Kaluthara | kaluthara | 732 athagama east | RC |  | 500000 | [12 empty] | 1
247 | Development of bikkhu Nikethanaramaya | Kaluthara | kaluthara | 729 c pulartan | RC |  | 200000 | [5 empty] | 1
248 | Development of Shakyasinghe Viharaya | Kaluthara | kaluthara | 729 I weniwalkatiya | RC |  | 200000 | [5 empty] | 1
249 | Development of Jayawardenarama Viharaya | Kaluthara | kaluthara | 731 kalamulla east | RC |  | 200000 | [5 empty] | 1
250 | Development of Kettharama Viharaya | Kaluthara | kaluthara | 727 mahawatta | RC |  | 200000 | [5 empty] | 1
251 | Development of Sri Sudarshanarama Viharaya | Kaluthara | kaluthara | 729 a alubogahalanda | RC |  | 200000 | [5 empty] | 1
252 | Development of Siri Sadaham Viharaya | Kaluthara | kaluthara | 729 I weniwalkatiya | RC |  | 300000 | [5 empty] | 1
253 | Development of the Mahimulla Sri Lankarama Viharaya | Kaluthara | kaluthara |  | RC |  | 200000 | [5 empty] | 1
254 | Development of Uttarachetiyarama Viharaya | Kaluthara | kaluthara | 701 a kudagonaduwa | RC |  | 200000 | [8 empty] | 1
255 | Development of the mosque , Saaviya | Kaluthara | kaluthara | 730 wettumakad | RC |  | 114000 | [7 empty] | 1
256 | Solar power facilities for Ganewatta Purana Viharaya | Kaluthara | kaluthara |  | RC |  | 500000 | [8 empty] | 1
257 | Providing drinking water to Delgahawaththa Road | Kaluthara | kaluthara | 700 mastiya | WS |  | 520469.3 | [5 empty] | 1
258 | Supplying drinking water to the by-road on the Kawatayagoda Pelawatta road | Kaluthara | kaluthara | 701 mahagonaduwa | WS |  | 136629.5 | [5 empty] | 1
259 | Supplying drinking water to Mahagerawatta road upto | Kaluthara | kaluthara | 705 a mawala south | WS |  | 143036.1 | [5 empty] | 1
260 | Supply drinking water to Maragahawatta Road | Kaluthara | kaluthara | 706 b moronthuduwa south | WS |  | 172926.7 | [5 empty] | 1
261 | Providing drinking water to Delduwa Navinna road | Kaluthara | kaluthara | 709 a delduwa | WS |  | 1246001.3 | [5 empty] | 1
262 | Completion of the supply of water for the Kalogoda polkanda dam | Kaluthara | kaluthara | 711 panapitiya south | WS |  | 549496.76 | [7 empty] | 1
263 | Providing of drinking water from Gunagoda to Kalapugama border | Kaluthara | kaluthara | 712 paraduwa | WS |  | 446659.5 | [5 empty] | 1
264 | Providing drinking water for near road at Dediyawala clinic | Kaluthara | kaluthara | 715 dediyawala | WS |  | 406922.1 | [5 empty] | 1
265 | Supplying drinking water to the area at Dodammulla mada para, Diyagama | Kaluthara | kaluthara | 713 a dodammulla | WS |  | 946461.85 | [5 empty] | 1
266 | Providing drinking water to the road behind the Pushparama Temple in Veyangoda | Kaluthara | kaluthara | 718 c vilegoda north | WS |  | 260579.7 | [5 empty] | 1
267 | Supplying drinking water to lintanwatta sewa piyasa | Kaluthara | kaluthara | 723 c godaparagahahena | WS |  | 25000
268 | Supplying drinking water to Richmondcort Estate, Panwila | Kaluthara | kaluthara | 723 f thekkawatta | WS |  | 470339.2 | [5 empty] | 1
269 | Providing drinking water facilities for the village of Tekawatta, Minuwan Udumulla | Kaluthara | kaluthara | 723 f thekkawatta | WS |  | 952801.5 | [5 empty] | 1
270 | Development of the rest of the work at the Kalugama Junior School and the play ground | Kaluthara | kaluthara | 709 c kalapugama west | PG |  | 1200000 | [5 empty] | 1
271 | Diyagama Maha Vidyalaya construction of a protective net around the playground | Kaluthara | kaluthara | 713 a dodammulla | PG |  | 1200000 | [10 empty] | 1
272 | Reconstruction of a playground for the Samanala playground | Kaluthara | kaluthara | 727 c kuruduwatta | PG |  | 1500000 | [5 empty] | 1
273 | Preparation of Gamassha De Silva Ground | Kaluthara | kaluthara | 729 e kajuduwawatta | PG |  | 1000000 | [8 empty] | 1
274 | Reconstruction and renovation of the Pakistan Kondapitiya playground | Kaluthara | kaluthara | 730 wettumakad | PG |  | 500000 | [13 empty] | 1
275 | Development of Kalamulla playground | Kaluthara | kaluthara | 731 a kalamulla south | PG |  | 650000 |  | nanda | [11 empty] | 1
276 | Construction of Children's Parks at Moronthuduwa, Kalapagama | Kaluthara | kaluthara | 709 c kalapugama west | PG |  | 1800000 |  |  |  |  | 1
277 | Construction of a toilets system at Musaeus College | Kaluthara | kaluthara | 731 a kalamulla south | SF |  | 400000 | [8 empty] | 1
278 | Reconstruction of toilets at the Roman Catholic College, Kalmulla | Kaluthara | kaluthara | 718 a jawatta | SF |  | 300000 | [5 empty] | 1
279 | ND Mr. Neil Gamini | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
280 | SA Mr. Athula Priyantha | Kaluthara | kaluthara | 729d galassa | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
281 | Mrs. Sunila Anoma Ranjani | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
282 | Mr. R. Sasath Silva | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
283 | Ṭi.ḍi. Ms. Chalonona died | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
284 | Mr. B. Sarath Silva | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
285 | Mr.k.m.p. Mendis | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
286 | W. Mrs. Gunawathie | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 | [7 empty] | 1
287 | Kē.kē.ē.bī. Mr. Adikaram | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
288 | Ē.ē.si.ḍi. Mr. Priyankara | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
289 | Ār.ḍi.ḍi. Mrs. Sandamali | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  |  |  | 1
290 | Mr. Wally Vitharana | Kaluthara | kaluthara | 729 d galassa | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
291 | Mrs. PU Mushushani | Kaluthara | kaluthara | 729 Kaduwuwatte | HD |  | 150000 |  |  |  |  | 1
292 | Mrs. MADevika Kumari | Kaluthara | kaluthara | 729 Kaduwuwatte | HD |  | 150000 | [7 empty] | 1
293 | Mrs. P. Samanthi Perera | Kaluthara | kaluthara | 729 Kaduwuwatte | HD |  | 150000 |  |  |  |  | 1
294 | Mrs. WAI Kusumalatha | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  |  |  | 1
295 | Mrs. A.A Gunawathi | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
296 | L.Dayani prithika | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 | [7 empty] | 1
297 | Mr. W.A.A.Kumarasinghe | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
298 | Mr. W.D.rusantha. | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  |  |  | 1
299 | Mrs. PVW Premawathie | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  |  |  | 1
300 | Mr. MKJayit | Kaluthara | kaluthara | 729 Veniwalaketiya | HD |  | 150000 |  |  |  |  | 1
301 | Ms. D.Kamala Nandani | Kaluthara | kaluthara | 729 Nagoda South | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
302 | Mr. EA Sirisena Ajith | Kaluthara | kaluthara | 705 maharakma | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1 |  |  |  | 1 |  |  |  |  | 1 st stage
303 | Mrs. D.D.G.Kumari perera | Kaluthara | kaluthara | 700 Mastia | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
304 | Mr. I.premarathna | Kaluthara | kaluthara | 700 Mastia | HD |  | 150000 |  |  |  |  | 1
305 | KB Ananda Perera | Kaluthara | kaluthara | 700 Mastia | HD |  | 300000 | [7 empty] | 1
306 | Mrs. K.nisanthanthi Surangika | Kaluthara | kaluthara | 700 Mastia | HD |  | 150000 | [7 empty] | 1
307 | Mrs. Hemawathi Jayasekara | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 | [7 empty] | 1
308 | M. Ms. Sumanawathie | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
309 | Jessica Benjamin | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
310 | Mr. KGS Gunarathna | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 | [7 empty] | 1
311 | Ms. K.Nanali Perera | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
312 | Mrs. Shyamali Dilhani | Kaluthara | kaluthara | 723, F teakwatta | HD |  | 150000 | [7 empty] | 1
313 | Nuwan Thushara de Alwis | Kaluthara | kaluthara | 723E palathota | HD |  | 150000 |  |  | 75000 |  |  |  |  | 1
314 | H.Cherpala promoter | Kaluthara | kaluthara | 701 a gonaduwa | HD |  | 300000 |  |  |  |  | 1
315 | Mrs. K. Niina Nirosha | Kaluthara | kaluthara | 718 Ethanamal | HD |  | 150000 | [7 empty] | 1
316 | H.a.m.c...perērā | Kaluthara | kaluthara | 718 a Jawatte | HD |  | 150000 | [7 empty] | 1
[7 empty] | 31841323.51 |  |  | 975000 |  | 17 | 28 | 0 | 27 | 8 | 0 | 1 | 2 | 1 | 3 | 87
* Projects should be categorized for following sectors | [6 empty] | ** Physical progress
a |  |  |  | Circular Code
RA- Rural Access |  |  |  | 2 | 3 |  | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  |  | 9 |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
SF- Sanitory Facility |  |  |  | 4 |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
PG- Play Ground |  |  |  | 5 |  |  | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  |  | 1 |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  |  | 7 |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
RC- Religious Center Development |  |  |  | 10 |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
SW- Social Welfare |  |  |  | 8 |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
HD- Housing Development |  |  |  | 12
SE- Sola Electricity |  |  |  | 11
WS- Rural Water Supply (Drinking water) |  |  |  | 6
OI- Other infastructure |  |  |  | 6

## WS
Gamperaliya- Rapid Rural Development Programme - 2019 | [16 empty] | Annexure D
Physical and Financial Progress of the Month of may 2019
District : KALUTHRA
No | Name of the Project | Electorate | DS Division | GN Division |  | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [12 empty] | No. of Beneficiaries | Remarks
[5 empty] | Sector |  |  |  |  | Financial |  | Physical **
[10 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
1 | Providing drinking water to Delgahawaththa Road | Kaluthara | kaluthara | 700 mastiya | WS |  | 300000 | [5 empty] | 1
2 | Supplying drinking water to the by-road on the Ketayagoda Pelawatta road | Kaluthara | kaluthara | 701 mahagonaduwa | WS |  | 250000 | [5 empty] | 1
3 | Supplying drinking water to Mahawerawatta road upto | Kaluthara | kaluthara | 705 a mawala south | WS |  | 200000 | [5 empty] | 1
4 | Supply drinking water to Maragahawatta Road | Kaluthara | kaluthara | 706 b moronthuduwa south | WS |  | 500000 | [5 empty] | 1
5 | Providing drinking water to Delduwa Navinna road | Kaluthara | kaluthara | 709 a delduwa | WS |  | 1000000 | [5 empty] | 1
6 | Completion of the supply of water for the Kalogoda polkanda dam | Kaluthara | kaluthara | 711 panapitiya south | WS |  | 800000 | [7 empty] | 1
7 | Providing of drinking water from Gunagoda to Kalapugama border | Kaluthara | kaluthara | 712 paraduwa | WS |  | 800000 | [5 empty] | 1
8 | Providing drinking water for Toragalla Budu Madura | Kaluthara | kaluthara | 712 paraduwa | WS |  | 800000 |  |  |  |  | 1
9 | Providing drinking water for near road at Dediyawala clinic | Kaluthara | kaluthara | 715 dediyawala | WS |  | 250000 | [5 empty] | 1
10 | Supplying drinking water to the area at Dodammulla mada para, Diyagama | Kaluthara | kaluthara | 713 a dodammulla | WS |  | 700000 | [5 empty] | 1
11 | Development of the Common Wells of the parana palliyawaththa | Kaluthara | kaluthara | 717 b thotupala | WS |  | 200000 |  |  |  |  | 1
12 | Providing drinking water to the road behind the Pushparama Temple in Veyangoda | Kaluthara | kaluthara | 718 c vilegoda north | WS |  | 200000 | [5 empty] | 1
13 | Supplying drinking water to Richmondcort Estate, Panwila | Kaluthara | kaluthara | 723 f thekkawatta | WS |  | 450000 | [5 empty] | 1
14 | Providing drinking water facilities for the village of Tekawatta, Minuwan Udumulla | Kaluthara | kaluthara | 723 f thekkawatta | WS |  | 850000 | [5 empty] | 1
15 | Supplying water from Gallassa junction to Veniewalaketiya | Kaluthara | kaluthara | 729 I weniwalkatiya | WS |  | 1000000 |  |  |  |  | 1
[7 empty] | 8300000 |  |  | 0 |  | 3 | 11 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 15
* Projects should be categorized for following sectors | [6 empty] | ** Physical progress
a |  |  |  | Circular Code
RA- Rural Access |  |  |  | 2 | 3 |  | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  |  | 9 |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
SF- Sanitory Facility |  |  |  | 4 |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
PG- Play Ground |  |  |  | 5 |  |  | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  |  | 1 |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  |  | 7 |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
RC- Religious Center Development |  |  |  | 10 |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
SW- Social Welfare |  |  |  | 8 |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
HD- Housing Development |  |  |  | 12
SE- Sola Electricity |  |  |  | 11
WS- Rural Water Supply (Drinking water) |  |  |  | 6
OI- Other infastructure |  |  |  | 6

## SF
Gamperaliya- Rapid Rural Development Programme - 2019 | [16 empty] | Annexure D
Physical and Financial Progress of the Month of may 2019
District : KALUTHRA
No | Name of the Project | Electorate | DS Division | GN Division |  | Length(k.m/m.)/ Area (/sq.m.) | Approved Amount (Rs, Mn.) | Implementing Agency | Name of the Contractor/ Society | Progress | [12 empty] | No. of Beneficiaries | Remarks
[5 empty] | Sector |  |  |  |  | Financial |  | Physical **
[10 empty] | Expenditure (Rs. Mn.) | % | A | B |  |  |  | C | D | E | F | G
[13 empty] | B1 | B2 | B3 | B4
271 | Construction of a toilets system at Musaeus College | Kaluthara | kaluthara | 731 a kalamulla south | SF |  | 400000 | [8 empty] | 1
272 | Reconstruction of toilets at the Roman Catholic College, Kalmulla | Kaluthara | kaluthara | 718 a jawatta | SF |  | 300000 | [5 empty] | 1
[7 empty] | 700000 |  |  | 0 |  | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 2
* Projects should be categorized for following sectors | [6 empty] | ** Physical progress
a |  |  |  | Circular Code
RA- Rural Access |  |  |  | 2 | 3 |  | A - Estimates are being / to be prepared
EL- Rural Electricity |  |  |  | 9 |  |  | B - For Constructions : B-1= Estimates Approved & Bid Documents Prepared, B-2= Quotation / Bid called, B-3= Quotation / Bid Received, B-4= Contract Awarded
SF- Sanitory Facility |  |  |  | 4 |  |  | Other: Identified Institutions/ CBO's to provide Goods / Instruments, Obtain required list of goods, Estimated prepared
PG- Play Ground |  |  |  | 5 |  |  | C - For Constructions : Start construction work,40% completed, Other : placed order for goods
MI- Minor Irrigation |  |  |  | 1 |  |  | D - For Constructions : 60% completed Other : Received goods /instruments as per the order
RE- Rural Economy |  |  |  | 7 |  |  | E - For Constructions 80% completed Other : Received goods /instruments as per the order
RC- Religious Center Development |  |  |  | 10 |  |  | F - For Constructions 99% completed Other : Completed lists of goods and beneficiaries
SW- Social Welfare |  |  |  | 8 |  |  | G - For Constructions 100 Completed Other : Issued goods and instruments to identified institutions/CBOs
HD- Housing Development |  |  |  | 12
SE- Sola Electricity |  |  |  | 11
WS- Rural Water Supply (Drinking water) |  |  |  | 6
OI- Other infastructure |  |  |  | 6